## Stakeholder Management Matrix
ML MODEL
POWER
INTREST
HIGH POWER, LOW INTEREST
High Power/High Interest
High Power/High Interest
HIGH POWER, HIGH INTEREST
LOW INTEREST, LOW POWER
HIGH INTEREST, LOW POWER
MDs , CEO
PRODUCT MANAGER , PRODUCT OWNER
SCRUM MASTER, DEVELOPER
DATA ANALYST ,TECH TEAM

## RACI matrix
Our product that requires modification to meet evolving customer needs and market demands. This feature change is crucial for staying competitive and maintaining customer satisfaction.
There needs to be a new software update where the customer can connect its device from its vehicle for ease of malfuntion detection, flexible mode of transactions and control, to cope-up with the market competition ,
Task/Activity | Product Manager | Develpoment team | Quality Assurance | Marketing team | Customer support
Define Feature Requirements | A | R | C | C | I
Develop Feature Implementation | R | A | I | C | C
Conduct Quality Testing | C | I | A | C | R
Create Marketing Strategy | I | C | C | A | R
Update Customer Support Materials | I | C | C | R | A
RESPONSIBLE
ACCOUNTABLE
CONSULTED
INFORMED

## Register
Stake holder name | Title | Role | Interest | Power | Requirements | Communication Plan | Column1
Mr Faizan khan | CEO | Chief Executive Officer | High | High | Strategic decisions | Monthly executive briefings
Mr Vineet Ravi | Senior Manager(M.D) | Head of Operations | High | High | Operational decisions | Bi-weekly operational updates
Mr Mithlesh.M | Product Manager | Product Management | High | Moderate | Model development | Regular technical discussions, progress reports
Ms Neha .K | Scrum Master | SOPs , Operations | High | Low | Implementing Agile Methodology | Weekly progress meetings
Ms Pratiksha S | Developer | Product Improvement | Moderate | Low | Ensure data readiness for ML model development | Techncal improvements
Mr Ishit Jain | Data Analyst | IT Specialist | Moderate | Moderate | Support integration and deployment of ML model | Updates on system requirements, testing, and deployment
Mr Pratik Jain | Customers | End Users (Delivery Recipients) | Low | Low | Delivery experience | Monthly customer feedback